## Planning Timeline
WMI Community Development Grant: Planning Timeline
Project Title:
Applicant Name:
Use the pull down and select the project stage to add to the timeline below. Review the example on tab two for further assistance.
Project Stages: Planning, Fundraising, Measurement & Evaluation, Implementation, Program Follow-Up, Program Reporting
Note: If you are applying in September 2024, you will receive funding at the start of January 2025. Plan your activities and completion dates in accordance.
Project Stage | Task Description | Responsible Person | Started on (DD/MM/YYYY) | Completion Due On (DD/MM/YYYY) | Result of the Task Completed
Planning
Planning
Fundraising
Implementation
Measurement & Evaluation
Program Follow-Up
Program Reporting

## Example Planning Timeline
WMI Community Development Grant: Planning Timeline
Project Title: Keeping an EYE on the Future (Eye exams, eye health seminars, and eyeglasses donation campaigns)
Applicant Name: Meg Akrumi
Note: These project stages are fictional and do not represent the full complexity WMI expects to see for an application. This example has been created to demonstrate how to utilize the template.
Project Stage | Task Description | Responsible Person | Started on (DD/MM/YYYY) | Completion Due On (DD/MM/YYYY) | Result of the Task Completed
Planning | Present project plan to doctors and ask them to volunteer for 2 days (dates to be determined) | Meg | 2025-01-16 | 2025-01-20 | Secure 7 doctors to volunteer for both events.
Planning | Approach community leaders in the 2 selected villages to get permission to host the event | Meg | 2025-01-20 | 2025-01-20 | Secure formal approval from the community leaders.
Planning | Confirm the in-kind donation of space from the secondary schools for both events | Meg | 2025-02-21 | 2025-02-26 | Receive written approval for the in-kind use of classrooms on event days.
Planning | Make a list of doctors and eyecare shops to approach for donations | Meg + Volunteer Doctors | 2025-02-27 | 2025-03-04 | Organized excel document with information about each location to approach and when.
Planning | Develop the curriculum for the vision seminar | Meg + Review by Volunteer Doctors | 2025-03-05 | 2025-03-20 | 3-hour interactive training on anatomy, basic eyecare, remedies to common issues, basic eye tests, Q&A, etc.
Planning | Create fliers, banners, and advertisements | Meg | 2025-03-25 | 2025-03-30 | Printed before deadlines set.
Planning | Purchase medical materials | Meg | 2025-04-02 | 2025-04-15 | Purchased in advance fo the first event.
Planning | Contract chair rentals | Meg | 2025-04-15 | 4/31/2025 | Pay deposit.
Fundraising | Receive notice of award decision from WMI | WMI | 2025-05-01 | 2025-05-31 | Receive notice of expected funds.
Fundraising | Provide all final documents to WMI for Community Development Grant funding | Meg | 2025-05-01 | 2025-05-30 | Complete funding responsibilities.
Fundraising | Receive donations from committed individuals and organizations | Meg | 2025-05-30 | 2025-05-15 | Deposit donations
Fundraising | Visit doctors and eye care shops to seek their involvement and donations | Meg + Volunteer Doctors | 2025-06-01 | 2025-06-15 | Receive donations
Measurement & Evaluation | Review M&E ideas with WMI | Meg | 2025-06-01 | 2025-06-20 | Receive formal feedback and plan for redesign.
Measurement & Evaluation | Make M&E tool draft | Meg | 2025-06-01 | 2025-06-05 | Five question questionnaire aligned with the developed training materials.
Measurement & Evaluation | Explain to all volunteers how they should use the M&E tools | Meg | 2025-06-01 | 2025-06-15 | All members of the project understand the importance of data tracking.
Implementation | Host introductory meeting to explain the opportunity, objectives, goals and responsibilities for those who volunteer | Meg | 2025-06-01 | 2025-06-15 | Everyone is aware of their responsibilities and all questions have been answered.
Implementation | Host the first vision health seminar | Meg + Local Volunteers | 2025-06-20 | 2025-06-20 | Implement the 3-hour session, have all participants complete the M&E tools, explain how the eye exam clinic will run on the following day.
Implementation | Host the first eye exam clinic | Meg + Volunteer Doctors + Local Volunteers | 2025-06-20 | 2025-06-20 | Implement the eye clinic with the assistance of trained volunteer doctors and collect M&E data.
Implementation | Evaluate how the running of the first events went and make notes on how to improve in the next community | Meg + Volunteer Doctors + Local Volunteers | 2025-07-21 | 2025-07-26 | Notes on how to modify the events for the second village.
Measurement & Evaluation | Review the M&E data from the first event | Meg | 2025-07-25 | 2025-07-25 | Adjust M&E tools as needed.
Measurement & Evaluation | Seek WMI assistance on how to best represent and share these results | Meg | 2025-08-02 | 2025-08-15 | Create a 1-page summary of results.
Measurement & Evaluation | Follow-up with patients who received eyeglasses | Meg | 2025-09-20 | 2025-09-30 | Document testimonials
Program Reporting | Begin working on the Three-Month Report to meet WMI requirements | Meg | 2025-10-01 | 2025-10-06 | Meet the deadline provided.
Program Reporting | Submit WMI Three-Month Report | Meg | 2025-11-07 | 2025-11-07 | Complete report following the guidelines and exceptional photographs supporting three-months worth of project progress.
Program Reporting | Submit WMI Six-Month Financial Report | Meg | 2025-12-31 | 2025-12-31 | Meet the deadline provided.
Program Reporting | Submit WMI Twelve-Month Financial Report | Meg | 2026-01-02 | 2026-01-07 | Complete report following the guidelines.

## Categories (hidden)
Planning Stages
Planning
Fundraising
Measurement & Evaluation
Implementation
Program Follow-Up
Program Reporting